## Action Plan
DIRECTIONS
Add the Event Name by replacing (Event) in A12
Add the Event Start Date in B14
Add the Event End Date in B15
Column D: Dates will automatically populate based on planning best practices. If you want to change the dates, just type the date into the cell
Column E: The teams that usually handle the tasks are added. If it's different, just change the name
Columns F, G, H: Add the people whose roles are to approve, be consulted or be informed. If you don't use these roles, you can leave the cells blank
Column I: Fill in the status of each activity
Column J: Fill in notes/comments
(Event) Action Plan Tracking
Updated (Date)
Event Start Date | 2021-11-01
Event End Date | 2021-11-04
Activity | Type | Phase | Date | Responsible | Approver | Consult | Inform | Status | Notes / Comments | Best Practice Timing | Timing
Receive rates and options from event manager | Event | Planning | 2021-05-17 | Marketing | [5 empty] | 6 months before | -24
Determine number of attendees allowed | Event | Planning | 2021-05-17 | Marketing | [5 empty] | 6 months before | -24
Receive rates and options from event manager | Presenting | Planning | 2021-05-17 | Marketing | [5 empty] | 6 months before | -24
Sign Contract/Return | Event | Planning | 2021-06-14 | Marketing | [5 empty] | 5 months before | -20
Sign Contract/Return | Presenting | Planning | 2021-06-14 | Marketing | [5 empty] | 5 months before | -20
Review booth graphics | Booth | Materials | 2021-08-09 | Marketing | [5 empty] | 3 months before | -12
Write and send Brief for Booth/Creative | Booth | Materials | 2021-08-09 | Marketing | [5 empty] | 3 months before | -12
Send information about presentation | Presenting | Planning | 2021-08-09 | Marketing | [5 empty] | 3 months before | -12
Confirm session time with event | Presenting | Planning | 2021-08-09 | Marketing | [5 empty] | 3 months before | -12
Create presentation | Presenting | Planning | 2021-08-09 | Marketing | [5 empty] | 3 months before | -12
Creative Presentation | Booth | Materials | 2021-08-23 | Marketing | [5 empty] | 10 weeks before | -10
Leadership Review & Feedback | Booth | Planning | 2021-08-23 | Event Leader | [5 empty] | 10 weeks before | -10
Determine who is attending | Event | Planning | 2021-08-30 | Marketing | [5 empty] | 9 weeks before | -9
Update/print booth graphics if necessary | Booth | Materials | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Create Event Plan | Event | Planning | 2021-09-06 | Event Leader | [5 empty] | 8 weeks before | -8
Create Trade Show Checklist | Event | Planning | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Confirm Booth Location & Size | Event | Planning | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Confirm format, AV, etc | Presenting | Planning | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Review/Update presentation | Presenting | Planning | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Create Presentation Invitation / Raffle | Presenting | Planning | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Attendee List obtained (if possible) | Lead Gen | Pre-Event | 2021-09-06 | Marketing | [5 empty] | 8 weeks before | -8
Determine materials needed | Literature | Materials | 2021-09-13 | Marketing | [5 empty] | 7 weeks before | -7
Set Kick-off Meeting | Event | Planning | 2021-09-13 | Event Leader | [5 empty] | 7 weeks before | -7
Load attendee list into CRM | Lead Gen | Pre-Event | 2021-09-13 | Marketing | [5 empty] | 7 weeks before | -7
Send list to sales team | Lead Gen | Pre-Event | 2021-09-13 | Marketing | [5 empty] | 7 weeks before | -7
Register attendees | Event | Logistics | 2021-09-20 | Marketing | [5 empty] | 6 weeks before | -6
Schedule travel/hotels | Event | Logistics | 2021-09-20 | Marketing | [5 empty] | 6 weeks before | -6
Place order for booth needs (furniture, AV, etc). | Event | Logistics | 2021-09-20 | Marketing | [5 empty] | 6 weeks before | -6
Place order for booth shipping w/Event | Event | Logistics | 2021-09-20 | Marketing | [5 empty] | 6 weeks before | -6
Design/finalize presentation | Presenting | Planning | 2021-09-20 | Marketing | [5 empty] | 6 weeks before | -6
Write Pre/Post emails | Lead Gen | Post-Event | 2021-09-20 | Marketing | [5 empty] | 6 weeks before | -6
Share VIP Access with customers | Lead Gen | Pre-Event | 2021-09-20 | Sales | [5 empty] | 6 weeks before | -6
Identify customers attending | Lead Gen | Pre-Event | 2021-09-20 | Sales | [5 empty] | 6 weeks before | -6
Update/print materials if necessary | Literature | Materials | 2021-09-27 | Marketing | [5 empty] | 5 weeks before | -5
Coordinate/purchase monitor | Event | Logistics | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Ship Materials to people attending | Event | Logistics | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Pre-Event Meeting #1 | Event | Planning | 2021-10-04 | Event Leader | [5 empty] | 4 weeks before | -4
Final Leadership Approval | Event | Planning | 2021-10-04 | Event Leader | [5 empty] | 4 weeks before | -4
Submit presentation to event | Presenting | Planning | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Send Pre-Event message (all attendees) | Lead Gen | Pre-Event | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Contact current customers before show | Lead Gen | Pre-Event | 2021-10-04 | Sales | [5 empty] | 4 weeks before | -4
Print Presentation Invitation / Raffle | Raffle | Pre-Event | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Obtain a Raffle Container | Raffle | Pre-Event | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Secure Raffle prize | Raffle | Pre-Event | 2021-10-04 | Marketing | [5 empty] | 4 weeks before | -4
Prepare Booth for shipping | Booth | Logistics | 2021-10-11 | Marketing | [5 empty] | 3 weeks before | -3
Prepare materials for shipping | Event | Logistics | 2021-10-11 | Marketing | [5 empty] | 3 weeks before | -3
Print Raffle Entry Forms | Raffle | Logistics | 2021-10-11 | Marketing | [5 empty] | 3 weeks before | -3
Ship Materials to Event venue | Booth | Logistics | 2021-10-18 | Marketing | [5 empty] | 2 weeks before | -2
Confirm who has Laptop | Event | Logistics | 2021-10-18 | Marketing | [5 empty] | 2 weeks before | -2
Add Raffle Entries to Shipment | Raffle | Logistics | 2021-10-18 | Marketing | [5 empty] | 2 weeks before | -2
Pre-Event Meeting #2 | Event | Planning | 2021-10-18 | Event Leader | [5 empty] | 2 weeks before | -2
Pre-Event Training/Direction | Team | Planning | 2021-10-18 | Event Leader | [5 empty] | 2 weeks before | -2
Create & put Demo Video on thumb drive (if needed) | Booth | Pre-Event | 2021-10-18 | Marketing | [5 empty] | 2 weeks before | -2
Pre-Event Meeting #3 (Final) | Event | Planning | 2021-10-25 | Event Leader | [5 empty] | 1 week before | -1
Event Start | Event | Event | 2021-11-01 | Event Leader | [5 empty] | Event | 0
Send photos and videos to marketing during meeting | Event | Event | 2021-11-01 | Sales | [5 empty] | Event | 0
Post Raffle Sign at Booth with Entries | Raffle | Event | 2021-11-01 | Sales | [5 empty] | Event | 0
Collect Raffles | Raffle | Event | 2021-11-01 | Sales | [5 empty] | Event | 0
Take Raffle Entries to Booth | Raffle | Event | 2021-11-01 | Sales | [5 empty] | Event | 0
Bring thumb drive with presentation | Presenting | Logistics | 2021-11-01 | Marketing | [5 empty] | Event | 0
Pick Raffle Winner and send email to marketing | Raffle | Post-Event | 2021-11-01 | Sales | [5 empty] | Event | 0
Event End | Event | Event | 2021-11-04 12:00 | Event Leader | [5 empty] | Event | 0.5
Confirm that Materials were returned | Booth | Logistics | 2021-11-08 | Marketing | [5 empty] | 1 week after | 1
Complete Recap | Event | Post-Event | 2021-11-08 | Sales | [5 empty] | 1 week after | 1
Recap Meeting | Event | Post-Event | 2021-11-08 | Event Leader | [5 empty] | 1 week after | 1
Send Post-Event emails (people we didn't meet) | Lead Gen | Post-Event | 2021-11-08 | Marketing | [5 empty] | 1 week after | 1
Make Post-Event email/calls (people we meet) | Lead Gen | Post-Event | 2021-11-08 | Sales | [5 empty] | 1 week after | 1
Notify & Send Prize to Raffle Winner | Raffle | Post-Event | 2021-11-08 | Marketing | [5 empty] | 1 week after | 1
Formulas:
Date = B14+([Timing]*7)

## Items
Event Booth Elements, Literature & Promo Items
Item | Type | Quantity | Price | Total Cost | Date | Responsible | Notes
| Give-aways |  |  | 0
| Booth elements |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0